## Project chart
ISMS Implementation Project For DamnArt
PROJECT TITLE |  | ISMS Implementation Project |  |  |  |  | COMPANY NAME | [7 empty] | Damnart
PROJECT MANAGER | [6 empty] | DATE | [7 empty] | 2026-03-31
WBS NUMBER | TASK TITLE | Reponsible Party | START DATE | DUE DATE | DURATION | % OF TASK COMPLETE | PHASE ONE | [17 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 | [5 empty] | WEEK 2 | [5 empty] | WEEK 3 | [5 empty] | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Introduction
1.1 | Initiate ISMS Project |  | 2026-03-31 | 2026-04-01 | 0 | 100 | bar: WEEK 1 M to WEEK 2 T
1.1.1 | Conduct Management Awareness session |  |  |  | 0 | 100 | bar: WEEK 1 T to WEEK 2 T
1.2 | Secure Management Consultant |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
1.3 | Understand Organization Context |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
1.4 | Define ISMS Scope |  |  |  | 0 | 100 | bar: WEEK 1 F to WEEK 2 W
2 | Execution
2.1 | Conduct Gap Assesment |  |  |  | 4 | 100 | bar: WEEK 1 F to WEEK 2 R
2.2 | Develop Risk Management Process |  |  |  | 3 | 0% | bar: WEEK 1 F to WEEK 2 T
2.3 | Conduct Risk Assesment |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
2.4 | Develop Statement of Applicability |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
3 | Implementation
3.1 | Develop Information Security Policies |  |  |  | 0 | 20 | bar: WEEK 1 F to WEEK 2 T; WEEK 2 S
3.2 | Develop Supporitng Procedures |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
3.2.1 | Implement Selected Controls |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
3.2.2 | Conduct Awareness and trainings sessions |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
4 | Monitoring
4.1 | Monitor and Measures ISMS Performance |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
4.2 | Conduct Internal Audits |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
4.3 | Coonduct Mangement Review |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
4.4 | Treat Non Confirmations |  |  |  | 0 | 0% | bar: WEEK 1 F to WEEK 2 T
4.5 | Implement Continual Improvement | bar: WEEK 1 F to WEEK 2 T
4.6 | Prepeare for Ceritifications Audit | bar: WEEK 1 F to WEEK 2 T

## Risk Assesment scenario Based
Scenario Based Risk Assesment
Scenario | Threat | Vulnerability | Likelihood | Impact | Current Control | Treatment | ISO Annex A Control | Residual Risk
1. Phishing Attack Leading to Credential Compromise | Attackers trick employees into revealing login credentials | Lack of phishing awareness; no multi-factor authentication (MFA) | Likely | High | Basic password policies; minimal training | Mitigate | A.7.2.2: Information security awareness, education, and training; A.9.4.1: Management of secret authentication information (implement MFA); A.12.2.1: Protection against malware (email filtering) | Medium
2. Ransomware Infection Disrupting Operations | Malware encrypt the data | Outdated antivirus software; lack of regular backups | Possible | High | Basic antivirus; irregular backups | Mitigate | A.12.2.1: Protection against malware (updated antivirus); A.12.3.1: Information backup; A.12.6.1: Management of technical vulnerabilities (patch management) | Low
3. Data Breach via Compromised Third-Party Vendor | Attackers exploit vendor’s weak security to access company data | No vendor security assessment; excessive data sharing | Possible | Major | None | Mitigate | A.15.1.1: Information security in supplier relationships; A.15.1.2: Addressing security within supplier agreements; A.13.2.4: Confidentiality or non-disclosure agreements | Low
4. Insider Threat Leading to Data Theft | Disgruntled employee steals sensitive data | Excessive access privileges; lack of monitoring | Unlikely | High | Basic access controls | Mitigate | A.9.2.3: Management of privileged access rights; A.12.4.1: Event logging; A.7.1.1: Screening (background checks) | Medium
5. Denial of Service (DoS) Attack Disrupting Web Services | Attack overwhelms web server, causing downtime | No DoS protection mechanisms in place | Possible | Moderate | Basic firewall | Mitigate | A.13.1.1: Network controls (DoS protection measures); A.13.1.3: Segregation in networks (use of WAF); A.16.1.5: Response to information security incidents | Low
6. Loss of Data Due to Natural Disaster | Flood or fire destroys physical hardware | No disaster recovery plan; data not backed up offsite | Unlikely | Severe | Onsite backups only | Mitigate | A.17.1.1: Planning information security continuity; A.17.2.1: Availability of information processing facilities (offsite backups); A.17.1.3: Verify, review, and evaluate information security continuity | Low

## Asset Based Risk Assesment
Asset Based Risk Assesment
Asset | Threat | Vulnerability | Likelihood | Impact | Risk Level | Current Control | Treatment | ISO Annex A Control | Residual Risk
Web Server (Hosted on Cloudways, hostinger) | Unauthorized access by external attackers | Weak password policy; no two-factor authentication | Medium | High | High | Basic password protection | Mitigate | A.9.2.1: User access management; A.9.4.1: Management of secret authentication information (implement MFA); A.13.1.1: Network controls (firewalls) | Medium
Cloud CRM System | Data breach leading to loss of customer data | Misconfigured access controls; lack of encryption | Medium | High | High | Limited access controls | Mitigate | A.9.2.3: Management of privileged access rights; A.10.1.1: Policy on the use of cryptographic controls (encrypt data); A.12.4.1: Event logging (security audits) | Low
Employee Laptops | Loss or theft of devices | Unencrypted hard drives; no device tracking | High | High | High | Password protection only | Mitigate | A.8.2.3: Handling of assets (implement encryption); A.9.4.1: Management of secret authentication information; A.11.2.6: Secure disposal or reuse of equipment (remote wipe capabilities) | Medium
Employee Computer | Malware infection via phishing emails | No antivirus software; users lack security awareness | Medium | Medium | Medium | None | Mitigate | A.12.2.1: Protection against malware; A.7.2.2: Information security awareness, education, and training; A.12.1.3: Capacity management (email filtering) | Low
Google Accounts | Credential theft through phishing attacks | No two-factor authentication; weak passwords | High | High | High | Basic password policy | Mitigate | A.9.2.1: User access management (strong password policy); A.9.4.1: Management of secret authentication information (implement MFA); A.7.2.2: Information security awareness, education, and training | Medium

## ISMS Gap Assesment
ISMS Gap Assesment
Clause 4: Context of the Organization
Key Requirements, Documents Needed, and Evidence
Clause | Requirement | Documents Needed | Evidence to Confirm Compliance | Requirement Met
4.1 | Determine external and internal issues relevant to the ISMS objectives | Documented analysis of internal and external issues | - Meeting minutes or records - Stakeholder analysis reports | yes
4.2 | Identify stakeholders and their information security requirements | List of interested parties and their requirements | - Stakeholder analysis reports - Communication records | yes
4.3 | Define the boundaries and applicability of the ISMS | ISMS scope document | - Approved ISMS scope statement - Organizational charts | yes
4.4 | Establish, implement, maintain, and continually improve the ISMS | ISMS framework documentation | - Process maps - Evidence of ISMS implementation | yes
Clause 5: Leadership
Key Requirements, Documents Needed, and Evidence
Clause | Requirement | Documents Needed | Evidence to Confirm Compliance | Requirement Met
5.1 | Top management must demonstrate leadership and commitment to the ISMS | Evidence of leadership commitment | - Meeting minutes with top management - Signed statements - Communication records | yes
5.2 | Establish an information security policy aligned with the organization's objectives | Information security policy | - Signed information security policy - Communication to staff | yes
5.3 | Assign and communicate responsibilities for information security roles | Roles and responsibilities document | - Organizational charts with ISMS roles - Job descriptions - Communication records | yes
Clause 6: Planning
Key Requirements, Documents Needed, and Evidence
Clause | Requirement | Documents Needed | Evidence to Confirm Compliance | Requirement Met
6.1.1 | Plan actions to address risks and opportunities | - Documented risk assessment methodology | - Records showing planning activities - Risk assessment schedules | yes
6.1.2 | Establish and implement a risk assessment process | - Risk assessment methodology - Risk assessment reports/risk register | - Completed risk assessments - Risk register | working
6.1.3 | Implement a risk treatment process and select controls | - Risk treatment plan - Statement of Applicability (SoA) | - Approved risk treatment plans - Updated SoA
6.2 | Set measurable information security objectives and plans | - Information security objectives - Plans to achieve objectives | - Monitoring and measurement records - Meeting minutes discussing objectives
Clause 7: Support
Key Requirements, Documents Needed, and Evidence
Clause | Requirement | Documents Needed | Evidence to Confirm Compliance | Requirement Met
7.1 | Determine and provide necessary resources for the ISMS | - Resource allocation records | - Budget documents - Resource plans | no
7.2 | Ensure personnel are competent through education, training, or experience | - Competence and training records | - Training attendance sheets - Certificates
7.3 | Personnel must be aware of the information security policy, their contributions, and implications of non-compliance | - Awareness materials | - Communication records - Staff acknowledgements | yes
7.4 | Establish internal and external communications relevant to the ISMS | - Communication plan | - Communication logs - Meeting records
7.5 | Control the creation, updating, and control of documented information | - Document control procedures - Master list of documents and records | - Controlled documents with versioning - Access logs
Clause 8: Operation
Key Requirements, Documents Needed, and Evidence
Clause | Requirement | Documents Needed | Evidence to Confirm Compliance | Requirement Met
8.1 | Plan, implement, and control the processes needed to meet ISMS requirements | - Operational procedures - Change management procedures | - Logs of operational activities - Change requests and approvals
8.2 | Perform risk assessments at planned intervals | - Records of risk assessments | - Updated risk assessments - Risk assessment reports
8.3 | Implement the risk treatment plan | - Risk treatment plan | - Evidence of implemented controls - Monitoring reports
Clause 9: Performance Evaluation
Key Requirements, Documents Needed, and Evidence
Clause | Requirement | Documents Needed | Evidence to Confirm Compliance | Requirement Met
9.1 | Determine what needs to be monitored and measured, methods, and analyze results | - Monitoring and measurement plan | - Performance metrics and reports
9.2 | Conduct internal audits at planned intervals | - Audit program / audit plan | - Completed audit checklists - Audit findings and corrective actions
9.3 | Top management reviews the ISMS at planned intervals | - Management review procedure - Management review meeting minutes | - Action items from management reviews - Decisions made
Clause 10: Improvement
Key Requirements, Documents Needed, and Evidence
Clause | Requirement | Documents Needed | Evidence to Confirm Compliance | Requirement Met
10.1 | Address nonconformities and take action to prevent recurrence | - Nonconformity and corrective action procedure - Corrective action records | - Nonconformity reports - Records of corrective actions
10.2 | Enhance the suitability, adequacy, and effectiveness of the ISMS | - Improvement logs | - Continual improvement projects - Feedback mechanisms

## Statement of Applicability
Statement of Applicabiliity
Control Reference | Control Description | Applicability | Implementation Status | Justification for Inclusion/Exclusion
A.5 Organizational Controls
A.5.1 | Policies for information security | Yes | Yes | Core ISMS requirement, sets the foundation for information security governance
A.5.2 | Information security roles and responsibilities | Yes | Yes | Defines accountability and responsibilities, crucial for ISMS effectiveness
A.5.3 | Segregation of duties | Yes | Yes | Prevents conflicts of interest, important for protecting data integrity
A.5.4 | Management responsibilities | Yes | Yes | Ensures senior management supports ISMS, essential for overall effectiveness
A.5.5 | Contact with authorities | Yes | Yes | Required for regulatory compliance and incident response, especially in case of data breaches
A.5.6 | Contact with special interest groups | Yes | Yes | Maintains awareness of industry developments and threat intelligence
A.5.7 | Threat intelligence | Yes | Yes | Provides up-to-date threat data, essential in a consulting environment
A.5.8 | Information security in project management | Yes | Yes | Ensures security is considered in all client-related projects
A.5.9 | Inventory of information and other associated assets | Yes | Yes | Required for identifying and managing assets, especially in cloud-based and remote environments
A.5.10 | Acceptable use of information and other associated assets | Yes | Yes | Ensures employees handle information properly, critical in data handling and consulting
A.5.11 | Return of assets | Yes | Yes | Necessary for managing equipment (e.g., laptops) and access rights during employee offboarding
A.5.12 | Classification of information | Yes | Yes | Helps in prioritizing protection of sensitive client and internal information
A.5.13 | Labelling of information | Yes | Yes | Important for identifying sensitive information in cloud storage or shared drives
A.5.14 | Information transfer | Yes | Yes | Ensures secure information sharing, especially relevant in client interactions
A.5.15 | Access control | Yes | Yes | Fundamental for controlling access to sensitive data and systems
A.5.16 | Identity management | Yes | Yes | Ensures secure authentication practices, crucial in a remote work environment
A.5.17 | Authentication information | Yes | Yes | Protects credentials and authentication mechanisms from misuse
A.5.18 | Access rights | Yes | Yes | Ensures only authorized users can access sensitive client and corporate data
A.5.19 | Information security in supplier relationships | Yes | Yes | Important for managing security with cloud providers and third-party vendors
A.5.20 | Addressing information security within supplier agreements | Yes | Yes | Ensures cloud providers and partners meet required security standards
A.5.21 | Managing information security in the ICT supply chain | Yes | Yes | Important if third-party tools/software are used in service delivery
A.5.22 | Monitoring, review and change management of supplier services | Yes | Yes | Ensures suppliers adhere to required security standards as DamnArt
A.5.23 | Information security for use of cloud services | Yes | Yes | Ensures tools/software used in client services meet security requirements
A.5.24 | Information security incident management planning and preparation | Yes | Yes | Ensures readiness to manage security incidents effectively, prote4cting client's data and organizational integrity
A.5.25 | Assessment and decision on information security events | Yes | Yes | Enables timely evaluation and response to security events, minimizing client impact
A.5.26 | Response to information security incidents | Yes | Yes | Ensures incidents are managed in an organized manner, reducing operational and reputational risks
A.5.27 | Learning from information security incidents | Yes | Yes | Supports continual improvement by learning from past incidents
A.5.28 | Collection of evidence | Yes | Yes | Supports investigation and compliance requirements through proper evidence handling
A.5.29 | Information security during disruption | Yes | Yes | Ensures security remains effective during disruptions, supporting business continuity
A.5.30 | ICT readiness for business continuity | Yes | Yes | Ensures systems are prepared for disruptions and service continuity
A.5.31 | Legal, statutory, regulatory and contractual requirements | Yes | Yes | Ensures compliance with laws and data protection requirements
A.5.32 | Intellectual property rights | Yes | Yes | Protects proprietary content and methodologies used in consulting